## Sheet1
Day | Work completed | Important decision / outcome | Reason
1 | Reviewed final project requirements | Final Phronesis will combine a teacher-facing application with a substantial Data Science/ML component | Ensures the final system meets both the original Phronesis aims and the CM3005 Data Science template
1 | Reviewed and prioritised functional requirements | Core analytics, student profiles, dashboard, explanations and recommendations remain central; large MIS integrations remain out of scope | Prevents feature creep and keeps development achievable
1 | Designed final application data inputs | Phronesis will accept student, assessment, attendance, behaviour and homework data | Uses information schools can realistically obtain and minimises manual teacher input
1 | Designed flexible assessment/attendance structure | Multiple assessments and attendance periods can be added instead of restricting the system to fixed columns | Allows longitudinal analysis and future updates
1 | Considered sensitive/contextual information | SEN/FSM and similar characteristics will primarily be used for context/fairness rather than directly determining risk | Reduces potential bias and supports responsible educational AI
2 | Selected ML training dataset | UCI Student Performance student-por.csv selected as the experimental training dataset | Contains 649 secondary-school records and known academic outcomes
2 | Reviewed dataset variables | Identified academic/engagement variables and separated irrelevant or sensitive variables | Keeps the predictive model focused and interpretable
2 | Defined prediction target | G3 < 10 = At Risk; G3 ≥ 10 = Not At Risk | Provides a clear outcome for the classification experiment
2 | Investigated target distribution | 100 At Risk and 549 Not At Risk students identified | Revealed class imbalance that must be considered during evaluation
2 | Performed initial exploratory comparison | Earlier grades, previous failures, absences and study time were examined between the two groups | Checks whether potential predictors show meaningful differences before modelling
2 | Defined Experiment 1 | Use failures, absences and study time without G1/G2 | Tests whether academic risk can be detected earlier
2 | Defined Experiment 2 | Add G1 and G2 to the early-warning inputs | Tests how much previous assessment evidence improves prediction
2 | Planned engineered features | Grade change, grade average, previous-failure indicator and low-study-time indicator | Allows testing whether derived information improves model performance
3 | Set up Data Science project structure | Created separate folders for raw/processed data, notebooks, models, figures, results and development evidence while retaining the existing Phronesis prototype | Keeps experimental ML work organised without breaking the existing application and improves reproducibility
3 | Loaded and inspected student-por.csv | Confirmed the dataset contains 649 student records and 33 variables | Verifies the downloaded dataset before any transformations or modelling
3 | Performed data-quality checks | Confirmed 0 missing values and 0 duplicate rows | Ensures preprocessing decisions are based on the actual quality of the dataset rather than unnecessary cleaning
3 | Validated numerical and categorical ranges | Checked age, study time, failures, absences and G1/G2/G3 ranges and confirmed key school/sex categories were valid | Identifies impossible or suspicious values before analysis
3 | Created binary at_risk target | Converted final grade into G3 < 10 = At Risk; G3 ≥ 10 = Not At Risk | Converts the academic outcome into a clear binary classification problem
3 | Analysed class distribution | Confirmed 100 At Risk (15.41%) and 549 Not At Risk (84.59%) | Identified substantial class imbalance and showed that accuracy alone will be insufficient for evaluation
3 | Generated risk-distribution visualisation | Created a bar chart comparing At Risk and Not At Risk students | Provides visual evidence of the class imbalance for EDA/reporting
3 | Analysed first-period grades | Median G1 was 12 for Not At Risk and 8 for At Risk; produced a boxplot | Shows a strong difference in earlier attainment between the two outcome groups
3 | Analysed second-period grades | Mean G2 was 12.31 vs 7.53 and median G2 12 vs 8 for Not At Risk and At Risk respectively; produced a boxplot | Shows that assessment performance later in the year provides a strong risk signal
3 | Analysed previous academic failures | Created prevFailure; 9.29% of Not At Risk students versus 49% of At Risk students had a previous failure | Identified previous academic difficulty as a potentially strong early-warning feature
3 | Analysed school absences | Mean absences were 3.49 vs 4.61 and medians 2 vs 2.5 | Found that absences differ between groups, although much less strongly than grades or previous failures
4 | Investigated relationship between G1 and G2 | Found a strong positive correlation of r = 0.865 and produced a scatter plot | Shows that earlier assessment results are strongly related and should not be treated as independent evidence without consideration
4 | Engineered assessment-change feature | Created grade_change = G2 - G1 | Allows Phronesis to represent whether academic performance improved or declined
4 | Evaluated grade-change feature | Mean change was +0.25 for Not At Risk and −0.25 for At Risk; 27.69% vs 35% experienced a decline | Showed that grade change may provide some information but separates the groups less strongly than absolute G1/G2 performance
4 | Created assessment-average feature | Created grade_average from G1 and G2 | Provides a simplified representation of overall prior attainment for feature-engineering experiments
4 | Created EDA summary table | Consolidated G1, G2, previous failure, absences and grade-decline findings | Produces a concise evidence record linking exploratory analysis to later modelling decisions
4 | Refined operational feature selection | Removed studytime from the core Phronesis experiments because teachers would not normally supply reliable revision-hour data | Better aligns the experimental ML model with data the finished Phronesis system could realistically obtain with minimal teacher effort
4 | Finalised Experiment 1 | Failures + absences → At Risk prediction | Tests whether risk can be identified before assessment results are available
4 | Finalised Experiment 2A | Failures + absences + G1 + G2 → At Risk prediction | Tests how much previous assessment information improves risk prediction
4 | Finalised Experiment 2B | Previous-failure indicator + absences + grade average + grade change → At Risk prediction | Tests whether engineered, Phronesis-style summary features can represent assessment history effectively
4 | Prepared ML experiment datasets | Experiment 1 = 649 × 3, Experiment 2A = 649 × 5, Experiment 2B = 649 × 5 | Confirms all student records were retained while using different feature representations
4 | Created reproducible train/test splits | Used 80% training / 20% testing, random_state=42 and stratification for all experiments | Ensures fair and reproducible model comparisons while preserving the class distribution
4 | Verified split balance | Each experiment contains 519 training and 130 test students, with 15.41% At Risk in training and 15.38% in testing | Confirms stratification worked and each experiment will be evaluated on comparable data
5 | Created majority-class baseline | Baseline predicted every student as Not At Risk and achieved 84.62% accuracy but 0% precision, recall and F1 | Demonstrated that high accuracy can be misleading because the dataset is imbalanced
5 | Evaluated baseline using multiple classification metrics | Added accuracy, precision, recall, F1 and confusion matrix rather than relying on accuracy alone | Provides a more meaningful evaluation of At Risk identification
5 | Trained Logistic Regression on Experiment 1 | Default Logistic Regression using failures and absences achieved 83.08% accuracy, 0% recall and 0% F1 | Showed that these early-warning variables alone were insufficient for useful minority-class prediction with the default model
5 | Trained Logistic Regression on Experiment 2A | Adding G1 and G2 increased performance to 92.31% accuracy, 72.73% precision, 80% recall and 76.19% F1 | Demonstrated the substantial predictive value of previous assessment information
6 | Trained Logistic Regression on Experiment 2B | Engineered representation achieved 93.08% accuracy, 73.91% precision, 85% recall and 79.07% F1 | Produced the strongest Logistic Regression result on the current test split
6 | Compared Logistic Regression experiments | Experiment 2B performed slightly better than 2A while Experiment 1 remained weak | Identified a promising feature representation but highlighted the need for further validation
6 | Produced Logistic Regression confusion-matrix visualisations | Exp 1 detected 0/20, Exp 2A detected 16/20, and Exp 2B detected 17/20 At Risk test students | Provides visual evidence of how assessment information improves risk detection
6 | Saved Logistic Regression evaluation evidence | Created comparison results and saved figures/results for later evaluation | Preserves reproducible evidence for later model comparison
7 | Trained Decision Tree on Experiment 1 | Achieved 84.62% accuracy, 50% precision, 25% recall and 33.33% F1 | Decision Tree identified some At Risk students where Logistic Regression Exp 1 identified none
7 | Trained Decision Trees on Experiments 2A and 2B | Both produced 89.23% accuracy, 65% precision, 65% recall and 65% F1 | Assessment information again substantially improved prediction, while 2A and 2B produced identical test performance
7 | Investigated Decision Tree feature importance | G2 dominated Experiment 2A while grade average dominated Experiment 2B | Provided initial insight into which academic variables the tree relied upon
7 | Checked Decision Tree overfitting | Training accuracy was 98.65% for 2A and 98.46% for 2B, compared with 89.23% test accuracy | The gap suggested unrestricted Decision Trees were fitting the training data too closely
8 | Trained Random Forest on Experiment 1 | Achieved 83.85% accuracy, 45.45% precision, 25% recall and 32.26% F1 | Confirmed that limited early-warning features remained weak even with a more complex ensemble model
8 | Trained Random Forest on Experiment 2A | Achieved 89.23% accuracy, 65% precision, 65% recall and 65% F1 | Assessment information again produced a substantial improvement
8 | Trained Random Forest on Experiment 2B | Achieved 87.69% accuracy, 58.33% precision, 70% recall and 63.64% F1 | Detected slightly more At Risk pupils than 2A but produced additional false positives
8 | Compared three ML algorithms across all experiments | Logistic Regression Experiment 2B currently gave the strongest single-split result | Established a provisional best model while avoiding final model selection before stronger validation
8 | Created master model comparison | Combined baseline, Logistic Regression, Decision Tree and Random Forest results into one results table | Allows direct comparison of algorithms, feature representations and classification metrics
8 | Identified overall modelling pattern | Experiment 1 was weak across all algorithms, while assessment-informed Experiments 2A/2B performed substantially better | Suggests previous assessment performance is important for academic-risk prediction in this dataset
9 | Applied 5-fold stratified cross-validation to Logistic Regression, Decision Tree and Random Forest using Experiments 2A and 2B | Logistic Regression 2B produced the strongest overall average performance, while Random Forest 2B achieved the highest default recall | Provides a more reliable comparison than relying on one train/test split and tests model stability across multiple folds
9 | Calculated mean and standard deviation for accuracy, precision, recall, F1 and ROC-AUC | Logistic Regression showed strong overall performance and stable ROC-AUC, while recall varied more between folds | Measures both average performance and consistency across validation folds
9 | Compared raw assessment features with engineered features | Experiment 2B performed slightly better overall, but differences from 2A were small | Shows that engineered grade-average and grade-change features provide a useful alternative representation without overstating their benefit
9 | Investigated class imbalance using balanced Logistic Regression and Random Forest models | Balancing substantially improved recall for At Risk students, especially for Random Forest | The dataset contains far fewer At Risk students, so class weighting was tested to reduce missed positive cases
10 | Compared default and balanced model performance | Balanced Random Forest 2B achieved the strongest recall and improved F1, while default Logistic Regression retained higher precision | Demonstrates the trade-off between detecting more At Risk students and increasing false-positive alerts
10 | Generated out-of-fold Logistic Regression probabilities for threshold analysis | Threshold evaluation was performed without using the final test set | Prevents test-set leakage and allows threshold decisions to be based on cross-validated training predictions
10 | Evaluated classification thresholds of 0.30, 0.40, 0.50 and 0.60 | A 0.40 threshold provided a strong balance between precision, recall and F1 compared with the default 0.50 threshold | Investigates whether Phronesis can detect more At Risk students without creating an excessive number of false alerts
10 | Compared confusion matrices at different thresholds | Lowering the threshold from 0.50 to 0.40 identified four additional At Risk students while creating only two additional false positives | Provides a practical interpretation of the precision-recall trade-off in terms of actual student classifications
10 | Investigated Decision Tree complexity using different maximum depths | A maximum depth of 2 produced substantially better recall, F1 and ROC-AUC than the unrestricted tree | Supports the earlier indication of overfitting and shows that controlling model complexity improves generalisation
10 | Identified models to carry forward for final evaluation | Logistic Regression 2B, Balanced Random Forest 2B and depth-2 Decision Tree 2B remain the main candidates | Narrows the next stage to the strongest and most practically relevant models before final model selection and explainability work
11 | Compared the final candidate models using pooled out-of-fold training predictions | Logistic Regression 2B at 0.40, Balanced Random Forest 2B and depth-2 Decision Tree 2B were compared using accuracy, precision, recall, F1 and ROC-AUC | Provides a fair comparison using predictions generated from cross-validation rather than relying on a single train/test split
11 | Performed false-negative and false-positive error analysis on the strongest models | The models made different types of errors, with Logistic Regression producing fewer false positives while the Random Forest and Decision Tree detected more At Risk students | Helps evaluate the practical consequences of model errors rather than comparing metrics alone
11 | Identified students missed by all three candidate models | Six At Risk students were missed by Logistic Regression, Random Forest and Decision Tree, with most having borderline previous attainment values | Shows that some errors are caused by limitations in the available predictive features rather than one particular algorithm
11 | Added Average Precision as an additional evaluation metric | Logistic Regression produced the strongest Average Precision, while the tree and forest still provided stronger recall at their selected thresholds | Provides a metric focused on performance for the minority At Risk class and strengthens evaluation of the imbalanced dataset
11 | Performed Decision Tree hyperparameter tuning using 5-fold cross-validation | Very shallow trees performed best and depth 2 was retained over depth 1 despite identical classifications because depth 2 produced stronger ROC-AUC and Average Precision | Reducing tree complexity helps control overfitting while retaining more useful ranking information
11 | Tuned the Random Forest using GridSearchCV on training data only | The strongest configuration used 200 trees, no maximum depth, min_samples_leaf=10 and no class weighting | Hyperparameter tuning improved the balance between precision and recall without using the holdout test set for model selection
11 | Generated out-of-fold predictions for the tuned Random Forest | The tuned forest achieved approximately 0.942 accuracy, 0.778 precision, 0.875 recall and 0.824 F1 | Confirms that Random Forest tuning substantially improved performance compared with the earlier forest configurations
12 | Performed Logistic Regression hyperparameter tuning | The strongest unscaled configuration used C=10 with balanced class weights, but its overall F1 did not outperform the existing 0.40 threshold Logistic Regression | Shows that hyperparameter optimisation does not necessarily produce a better operational model
12 | Repeated Logistic Regression tuning using a StandardScaler Pipeline | Scaling changed the selected regularisation value to C=100 but the best mean cross-validation F1 remained approximately 0.7644 | Checks whether differences in feature scales affected regularised Logistic Regression while preventing preprocessing leakage during cross-validation
12 | Selected the three final model candidates | Logistic Regression 2B at 0.40, Decision Tree 2B depth 2 and tuned Random Forest 2B were retained for the final comparison | These represented the strongest combinations of precision, recall, F1, ranking performance and practical usability
12 | Created and saved the final three-model comparison | Tuned Random Forest achieved the highest pooled OOF accuracy and F1, while retaining high recall and strong ROC-AUC and Average Precision | Provides evidence for selecting a final model using several performance measures rather than accuracy alone
12 | Selected and froze the tuned Random Forest as the final model | The final configuration used 200 trees, no maximum depth, min_samples_leaf=10, no class weighting and a 0.50 classification threshold | Freezing the configuration before final evaluation prevents further tuning based on holdout performance
12 | Evaluated the frozen Random Forest on the final holdout test set | The model achieved 88.46% accuracy, 58.06% precision, 90% recall, 70.59% F1, 0.932 ROC-AUC and 0.852 Average Precision | Provides a final check of how the selected model generalises to data not used for its final parameter selection
12 | Analysed the final holdout confusion matrix | The model correctly identified 18 of 20 At Risk students, missing 2 while producing 13 false-positive alerts | Gives a practical interpretation of the model's 90% recall and shows the cost of prioritising detection of At Risk students
12 | Calculated Random Forest built-in feature importance | grade_average was the dominant feature with approximately 82.7% of the total built-in importance | Identifies which predictors the final model relies on most heavily and improves model explainability
12 | Performed permutation importance on the holdout data | Shuffling grade_average caused by far the largest reduction in F1, while the other features produced little change | Provides an additional explainability method and supports the finding that previous attainment is the model's dominant predictive signal
12 | Evaluated probability quality using the Brier score | The final Random Forest achieved a Brier score of approximately 0.0639 | Assesses the quality of the model's probability estimates rather than only evaluating its binary classifications
12 | Performed a five-bin calibration analysis | Very low-risk predictions were well calibrated, but some middle probability ranges overestimated the observed proportion of At Risk students | Indicates that raw model probabilities should not be presented to teachers as precise probabilities of failure
12 | Defined how model output should be represented within Phronesis | Risk output should be used primarily as a risk score or category rather than claiming an exact percentage probability of failure | Prevents the system from presenting model confidence with more certainty than the calibration evidence supports
Day | Work completed | Important decision / outcome | Reason
13 | Designed the final Phronesis model adapter | Final model inputs were fixed as prev_failure, absences, grade_average and grade_change | Creates a clear bridge between normal school data and the four features expected by the trained Random Forest
13 | Defined the final assessment data structure | Assessment records now include student_id, subject, assessment_title, assessment_date, score, max_score and pass_mark | Provides enough information to calculate model features without requiring teachers to manually transform their data
13 | Defined assessment conversion onto the model's 0–20 scale | Assessment scores are converted using (score / max_score) × 20 | Keeps real school assessment data compatible with the 0–20 grade scale used during model training
13 | Defined the rules for grade_average and grade_change | The latest two valid assessments for the same subject are used | Mirrors the two prior grade periods represented by G1 and G2 in the research dataset while avoiding comparisons between unrelated subjects
13 | Defined the practical prev_failure proxy | prev_failure is set to 1 when an earlier assessment was below its pass mark | Provides a practical approximation of the UCI failures feature using information available within Phronesis
13 | Defined the attendance-to-model conversion | absences is calculated as total_sessions - sessions_attended | Avoids incorrectly converting attendance percentages into absence counts without knowing the number of sessions
13 | Defined missing-data behaviour | Students without the required assessment or attendance history receive Insufficient data for risk prediction | Prevents fabricated values such as zero being inserted into the model when evidence is missing
14 | Implemented the assessment adapter | Assessment records are validated, converted to the 0–20 scale, grouped by student and subject, sorted by date and transformed into model features | Automates the feature engineering required before assessment data can enter the Random Forest
14 | Added subject-specific assessment processing | Assessments are grouped by both student_id and subject | Prevents Phronesis from treating performance changes between different subjects as a genuine grade trend
14 | Implemented calculation of prev_failure, grade_average and grade_change | Phronesis now generates the three assessment-derived ML features automatically | Removes the need for teachers to calculate machine-learning inputs manually
14 | Added safe assessment eligibility handling | Students with fewer than two valid assessments are retained but their assessment features are marked as unavailable | Ensures incomplete students remain visible while preventing unreliable model predictions
14 | Began separating model processing into adapter modules | Assessment, attendance and model-processing responsibilities were separated into dedicated files | Improves readability, maintainability and testing as the prototype develops into the final application
15 | Refactored the assessment processing code | process_assessments() now uses the same validation logic as validate_assessment_data() instead of duplicating rules | Reduces duplicated code and means future validation changes only need to be made once
15 | Completed assessment validation testing | 30 assessment tests passed across valid, invalid, missing, boundary and non-numeric inputs | Provides evidence that assessment data is checked before feature engineering
15 | Fixed future assessment date validation | A failed validation case showed that future assessment dates needed to be rejected, and the rule was corrected successfully | Prevents impossible future assessment results entering the prediction pipeline
15 | Implemented the attendance adapter | Attendance records are validated and converted into absences and attendance_percentage | Produces the model's required absence-count feature while retaining a teacher-friendly attendance percentage
15 | Completed attendance validation testing | All 15 attendance validation tests passed | Confirms invalid, missing and unrealistic attendance values are safely rejected
15 | Designed and implemented the final feature merge | The student roster is retained as the master source while assessment and attendance features are attached using student_id | Prevents students disappearing simply because one data source is missing
15 | Added prediction eligibility logic | Rows are marked Ready only when assessment and attendance data are valid and all four ML features are available | Ensures incomplete rows are never accidentally passed into the trained model
15 | Tested model-feature merging | Complete data, incomplete assessment data, missing attendance, no data and multiple-subject cases were tested successfully | Confirms the adapter behaves safely across the main real-world integration scenarios
16 | Connected the saved tuned Random Forest model | Phronesis loads final_random_forest_2b.joblib instead of retraining a model when the application starts | Ensures the final system uses the exact frozen model selected and evaluated during the ML stage
16 | Implemented real ML risk prediction | Only Ready rows are sent to the Random Forest using the four features in the original training order | Maintains consistency between model training and final application prediction
16 | Added safe handling for incomplete students | Students without enough information remain visible and receive Insufficient data instead of a prediction | Prevents misleading risk classifications based on incomplete records
16 | Produced the first genuine Phronesis Random Forest predictions | S002 was classified At Risk, while the other complete sample students were classified Not At Risk | Confirms that the trained Random Forest is genuinely driving the final system's risk classifications
16 | Added merge and prediction integration testing | Merge tests covered valid, incomplete, missing and multiple-subject cases, while prediction tests checked expected statuses and model outputs | Provides repeatable evidence that the complete model adapter and prediction pipeline behave correctly
16 | Created app_data.py | A single load_app_data() function now performs data loading, feature processing, merging and model prediction | Prevents Streamlit pages from duplicating the same backend-processing logic
16 | Connected the backend ML pipeline to the Streamlit application | The live app successfully displays Random Forest results from load_app_data() | Moves the project from standalone model testing into the actual final application
16 | Replaced the prototype dashboard risk categories | The dashboard now uses At Risk, Not At Risk and Insufficient data instead of the old High/Medium/Low rule-based categories | Ensures the interface reflects the actual trained model rather than the original prototype scoring system
16 | Added the new ML dashboard student table | The app displays student, subject, attendance, eligibility and Random Forest prediction while retaining incomplete students | Gives teachers a clear overview of actual model outputs and makes incomplete-data cases visible
17 | Added downloadable CSV templates for core school data | Teachers can download the expected formats for subjects, classes, students, assessments and attendance before preparing uploads | Reduces formatting errors and makes Phronesis easier to use without requiring teachers to understand the internal data structure
17 | Implemented Subject CSV upload | Teachers can bulk-add subjects using a CSV instead of entering every subject manually | Makes initial school setup faster and more practical for larger datasets
17 | Added validation to Subject CSV uploads | Missing columns, blank subject names and duplicate/existing subjects are handled before new subjects are saved | Prevents malformed or duplicated subject records from entering the application data
17 | Implemented Class CSV upload | Teachers can bulk-create classes containing class name, subject and year group information | Allows class structures to be created efficiently and links classes to existing subjects
17 | Added dependency validation for uploaded classes | Uploaded classes are only accepted when their referenced subject already exists and year-group values are valid | Maintains consistency between related school records and prevents broken class-subject relationships
17 | Implemented Student CSV upload | Teachers can upload multiple students and assign each student to one or more existing classes | Provides a scalable alternative to manually adding individual students
17 | Added student-upload relationship checks | Student year groups are checked against the year groups of their selected classes and non-existent classes stop the upload | Prevents invalid student-class relationships and maintains consistent school structure
17 | Implemented Assessment CSV upload | Teachers can bulk-upload assessment results containing student, class, assessment date, score, maximum score and pass mark | Allows real assessment histories to be added efficiently before the ML adapter generates model features
17 | Added detailed assessment-upload validation | Required fields, missing data, numeric values and impossible score ranges are checked before assessment records are accepted | Protects the later feature-engineering and prediction pipeline from invalid assessment data
17 | Implemented Attendance CSV upload | Teachers can bulk-upload total sessions and sessions attended for existing students | Allows Phronesis to generate the absences model feature from teacher-supplied attendance records
17 | Added attendance-upload validation | Uploaded attendance checks required columns, numeric and whole-number session values, logical session ranges, valid student IDs and duplicate records | Prevents impossible attendance information from reaching the Random Forest pipeline
17 | Integrated bulk upload alongside manual data entry | Teachers can now either enter school data manually through Phronesis or use downloadable templates and CSV uploads | Supports different teacher workflows while keeping both methods connected to the same underlying application data
17 | Prepared CSV upload functionality for systematic testing | Core validation rules have been implemented, but thorough input and edge-case testing remains the next development task | Separates implementation from verification and ensures the final testing evidence reflects actual tested behaviour rather than assumed correctness
18 | Began systematic Data Management testing after the bulk-upload implementation | Testing moved from feature creation to checking real user inputs, edge cases and failure handling | Provides evidence that the data-entry tools behave correctly rather than assuming that implemented validation works
18 | Completed focused testing of Subject management | Manual add, rename, delete and CSV upload behaviour were checked, including empty values and duplicate subjects | Subjects are the first dependency for classes, so errors here would affect the rest of the school-data structure
18 | Fixed Subject duplicate detection for inconsistent whitespace and capitalisation | Subject names are normalised before duplicate comparison | Prevents entries such as differently spaced versions of the same subject being stored as separate records
18 | Confirmed dependency protection when deleting Subjects | A subject cannot be deleted while an existing class still references it | Prevents broken class-to-subject relationships
18 | Continued using a test → fail → fix → retest workflow | Bugs found during testing are recorded before being corrected and retested | Produces clearer development evidence and shows how the system improved through testing
19 | Completed focused testing of Class management | Class add, edit, delete and CSV upload flows were exercised using normal and invalid inputs | Checks that class setup remains reliable before students and results are attached
19 | Fixed duplicate Class detection with extra internal spaces | Class names are cleaned before case-insensitive duplicate checks | Stops visually identical classes such as differently spaced versions of 7B Maths being created twice
19 | Added protection against deleting a Class containing students | Deletion is blocked when class_students contains students assigned to the selected class | Prevents students being left linked to a class that no longer exists
19 | Retained subject and year-group links when creating and editing Classes | Classes continue to store subject_id and year_group rather than duplicating subject information | Keeps the relational data structure consistent and avoids unnecessary duplication
19 | Identified remaining class-integrity edge cases for later review | Testing highlighted that changes affecting class year group may need to be considered alongside already assigned students | Separates completed functionality from lower-priority integrity improvements instead of silently assuming every case is solved
20 | Completed focused testing of Student management | Student add, edit and CSV upload workflows were tested with class assignments and validation rules | Students connect the class structure to assessment and attendance data, so relationship checks are essential
20 | Enforced the rule that a student cannot be assigned to two classes for the same subject | Selected classes are checked by subject_id before the student is saved | Prevents duplicate subject enrolment from producing ambiguous subject-specific analytics
20 | Improved Student and class-name whitespace handling | Extra spaces are removed from names and uploaded class lists before validation | Makes uploads more tolerant of realistic formatting mistakes without creating duplicate records
20 | Kept duplicate student names valid while preserving unique student IDs | Students are identified by student_id rather than assuming names are unique | Reflects realistic school data where different students may share the same name
20 | Ensured class_students is updated when Student class assignments change | Old class links are removed and the newly selected links are saved | Keeps student-to-class relationships synchronised after edits
21 | Completed focused testing of Assessment management | Manual entry, editing, deletion and CSV upload were tested across valid and invalid assessment records | Assessment history directly produces three Random Forest features, so bad records must be rejected before prediction
21 | Strengthened Assessment numeric and range validation | Scores, maximum scores and pass marks are checked for missing, non-numeric and impossible values | Prevents invalid marks from corrupting grade_average, grade_change and prev_failure
21 | Strengthened Assessment date validation | Invalid dates and future assessment dates are rejected | Keeps longitudinal trends based only on plausible completed assessments
21 | Improved duplicate Assessment detection | Duplicate checks use student, subject, cleaned assessment title and assessment date | Prevents the same result being entered twice while still allowing different assessments for the same student
21 | Kept Assessment processing subject-specific | Assessment records continue to derive their subject through the selected class and subject relationship | Prevents results from unrelated subjects being combined into one academic trend
22 | Completed focused testing of Attendance management | Attendance add, edit, delete and CSV upload flows were checked using valid and invalid records | Attendance supplies the absences feature used by the Random Forest and therefore requires reliable validation
22 | Added detailed Attendance upload validation | Session values must be numeric whole numbers, total sessions must be positive and sessions attended cannot exceed the total | Prevents impossible attendance records from entering the analytics pipeline
22 | Added duplicate and student-ID checks for Attendance uploads | Uploads reject repeated student rows, unknown student IDs and students who already have attendance records | Maintains one current attendance record per student and avoids conflicting inputs
22 | Preserved teacher-friendly attendance information alongside model features | Phronesis calculates attendance percentage for display while the adapter calculates absences for the model | Separates the information teachers need to read from the representation required by the trained model
22 | Brought the core Data Management area to a stable functional state | Subjects, classes, students, assessments and attendance can now be entered manually or uploaded with validation | Provides a complete input workflow for the final application before concentrating on analytics pages
23 | Built the combined Class Overview workflow | Teachers select Year Group, Subject and Class before viewing class-level analytics | Creates a clear drill-down path and avoids showing unrelated students or subjects together
23 | Added class summary metrics | The page reports class size, prediction readiness and At Risk information for the selected class | Gives teachers a quick overview before examining individual pupils
23 | Added a selectable student table within each class | Teachers can select one student directly from the class table to open their detailed profile below | Removes the need for a separate disconnected Students page and keeps the analysis in context
23 | Corrected class At Risk percentage calculation | At Risk percentage uses students with prediction_status Ready as the denominator | Prevents students with Insufficient data from distorting the model-risk percentage
23 | Converted internal model grades to teacher-friendly percentages in the interface | 0–20 grade_average and grade_change values are displayed as percentage equivalents | Keeps the ML representation internal while presenting familiar school measures to teachers
24 | Expanded the individual student profile inside the Class page | Selected students now show prediction status, risk output and key academic and engagement indicators | Brings the identify → understand → recommend workflow into one screen
24 | Implemented rule-based student Insights | Attendance, academic performance, grade change, previous failure, homework and behaviour can generate contextual observations when data is available | Helps teachers interpret the wider student picture without claiming that every contextual factor drove the Random Forest
24 | Implemented student Recommendations | Recommendations map identified concerns to practical follow-up actions such as attendance review, academic support and monitoring | Turns analytics into teacher-facing decision support rather than only displaying a prediction
24 | Added editable parent communication | Phronesis can generate a draft parent email from the selected student's current information for the teacher to review and edit | Supports follow-up while keeping the teacher responsible for the final communication
24 | Clarified the boundary between model inputs and contextual indicators | The Random Forest remains limited to prev_failure, absences, grade_average and grade_change; homework and behaviour are supporting context only | Maintains methodological consistency with the trained model and avoids misleading explanations
25 | Completed the main Dashboard structure | The Dashboard now provides an overall summary followed by priority students, insights, class summaries and charts | Creates a low-cognitive-load starting point for teachers after signing in
25 | Added Students Requiring Attention | At Risk predictions are surfaced in a priority table with class, subject, attendance and assessment context | Makes the most actionable cases visible without requiring teachers to open every class first
25 | Added Quick Insights for attendance, academic, homework and behaviour concerns | Contextual concern counts are shown only when the relevant data is available | Provides a wider overview while handling optional data safely
25 | Added My Classes summary and filters | Class-level risk, insufficient-data, attendance and assessment information can be filtered by year group and subject | Allows teachers to compare their classes and move from whole-workspace overview to a specific class
25 | Added class risk and attendance charts | The Dashboard visualises classes with the highest At Risk proportions and the lowest average attendance | Provides a compact visual comparison while retaining the text-first dashboard design
26 | Implemented teacher account creation and sign-in | A teachers.csv account file stores teacher ID, name, email, password hash and tutorial status | Adds authentication so Phronesis can provide a protected teacher workspace
26 | Added separate Sign In and Create Account flows | Users must authenticate before the normal Dashboard, My Classes, Data Management and Settings navigation is available | Prevents application pages and class data from appearing on the public login screen
26 | Added a first-login tutorial | New teachers see a short introduction to Dashboard, Classes, Data Management and recommendations before entering the app | Improves onboarding and explains the intended workflow before users begin uploading data
26 | Added Settings and account controls | Teachers can update their name, change password, reopen the tutorial and log out | Provides the basic profile and session controls expected in the final application
26 | Improved failed-login feedback | Unrecognised credentials return a clear email/password-not-recognised message and ask the user to try again | Gives useful feedback without exposing whether a specific email address exists
27 | Identified shared-data leakage between different teacher accounts | Authentication originally changed who was logged in, but every account still read the same global data/new CSV files | Showed that login alone was not enough to create independent teacher workspaces
27 | Designed a teacher-specific data-folder structure | Each teacher now uses a folder such as data/users/T001 containing their own students, subjects, classes, relationships, assessments and attendance files | Separates teacher-owned application data while retaining the existing simple CSV-based prototype architecture
27 | Created user_data.py helpers | get_user_file() resolves paths from the logged-in teacher_id and create_user_files() prepares empty CSV files with the correct headers | Centralises workspace path handling and avoids repeating account-folder logic across the application
27 | Changed app_data.py to load the logged-in teacher's files | Application analytics now use get_user_file() instead of fixed data/new paths for teacher-owned data | Ensures the Dashboard and Class analytics operate on the current teacher's workspace
27 | Converted Data Management modules to teacher-specific reads and saves | Subjects, Classes, Students, Assessments and Attendance were updated so both manual edits and CSV uploads use get_user_file() | Prevents one teacher's changes from intentionally writing into another teacher's application data
28 | Tested the application with a newly created empty teacher workspace | The new account exposed an empty-data edge case in the analytics pipeline | Testing with a realistic first-use state revealed behaviour that the original populated test dataset could not expose
28 | Diagnosed a KeyError on student_id during model-feature merging | An empty assessment dataset produced an empty assessment_features DataFrame with no column names | The merge expected student_id even when there were zero assessment rows
28 | Fixed empty Assessment feature output | process_assessments() now constructs its result with the expected student_id, subject, prev_failure, grade_average, grade_change and assessment_status columns even when there are no rows | Allows the model pipeline to handle a brand-new account without crashing during the merge
28 | Confirmed the application runs after the empty-data fix | The teacher-specific account setup can now reach the application without the previous student_id KeyError | Provides a stable baseline for continuing final testing and evidence collection
28 | Recorded authentication and workspace separation as the current development baseline | Future work can build on the completed login, tutorial, settings and user-specific data architecture rather than returning to the shared-data prototype | Reduces the risk of later changes accidentally undoing completed account and data-isolation work
29 | Improved the Assessment CSV template workflow | Assessment templates are now generated for a teacher-selected class rather than being downloaded as a completely blank file | Reduces manual setup and prevents teachers needing to remember internal student IDs
29 | Added student names alongside student IDs in Assessment templates | Each template row contains both student_id and the corresponding student name | Makes generated IDs understandable to teachers while continuing to use the unique ID internally
29 | Added an Assessment template setup popup | Teachers choose the class and enter assessment title, date, maximum score and pass mark before downloading the template | Allows information shared by the whole assessment to be entered once instead of repeatedly for every student
29 | Prefilled Assessment template information | Student ID, student name, class, assessment title, assessment date, maximum score and pass mark are automatically populated | Minimises repetitive data entry and reduces the chance of inconsistent assessment information
29 | Simplified the teacher's Assessment CSV task | score is deliberately placed as the final blank column so the teacher only needs to enter each student's result before uploading | Creates a quicker and more realistic workflow for entering whole-class assessment results
30 | Improved the Attendance CSV template workflow | Attendance templates can now be generated for a selected class through a popup | Makes attendance entry consistent with the improved Assessment workflow
30 | Added student and class information to Attendance templates | Student ID, student name and class name are automatically populated for every pupil in the selected class | Removes the need for teachers to look up student IDs or manually recreate their class roster
30 | Added Total Sessions to the Attendance template setup | The teacher enters the total number of sessions once before downloading and the value is copied to every student row | Avoids repeatedly entering the same attendance-period information
30 | Simplified the teacher's Attendance CSV task | sessions_attended is the final blank column, leaving only each student's attended-session value for the teacher to complete | Reduces teacher workload while retaining the information required to calculate absences and attendance percentage
30 | Added safe handling for classes with no students when generating templates | Template generation stops and informs the teacher when the selected class contains no students | Prevents empty or misleading CSV templates being downloaded
30 | Standardised bulk-data entry around prefilled templates | Assessment and Attendance downloads now prepare most of the required information automatically before the teacher edits the CSV | Improves usability and better reflects the aim of minimising unnecessary teacher data entry
Day | Work completed | Important decision / outcome | Reason
31 | Redesigned the public Phronesis landing page | Added a large branded hero area, classroom feature section, Why Phronesis cards, review placeholders, sign-up CTA and footer | Gives the finished system a more professional first impression before teachers sign in
31 | Improved public-page interaction and visual styling | Added rounded coloured cards, hover animations, shadows, wider layouts and clearer spacing between sections | Makes the interface feel more polished and easier to visually scan
31 | Removed fragile custom HTML from the landing page | Public content now uses native Streamlit components styled through keyed containers | Prevents HTML being displayed as text and keeps the interface more reliable
31 | Added clearer public explanation of Phronesis | Landing page explains how assessment, attendance and behaviour information supports identification and interpretation of student risk | Helps users understand the purpose of the system before creating an account
31 | Separated page-specific styling | About, login, tutorial and logged-in application styling are being separated into dedicated CSS files | Reduces CSS conflicts and makes the interface easier to maintain
31 | Began redesigning the Sign In/Create Account experience | Authentication is being updated to match the same Fredoka/Nunito, rounded and warm-colour visual theme as the landing page | Creates a consistent transition from the public site into the Phronesis application
Day | Work completed | Important decision / outcome | Reason
32 | Redesigned the Data Management interface | Subjects, Classes, Students, Assessments and Attendance were updated to use the same clean card-based layout | Creates a consistent interface and makes data-entry tasks easier to understand
33 | Standardised Data Management actions and popups | Add, edit, delete, template download and CSV upload actions were reorganised into consistent button rows and dialogs | Reduces clutter and makes repeated workflows more predictable for the teacher
34 | Redesigned the Class Overview page | Added class filters, summary metrics, student profile sections, risk status, indicators, insights, recommendations and parent communication | Makes the identify-understand-support workflow clearer and easier to follow
35 | Improved analytical table presentation | Added risk-based row highlighting for student analysis tables and kept Data Management tables neutral | Helps important risk information stand out without making administrative tables visually noisy
36 | Redesigned the Dashboard | Added compact summary cards, quick insights, priority student information, class summaries and improved spacing | Makes the main dashboard more useful as a quick overview and reduces unnecessary scrolling
37 | Improved dashboard visualisations and colour scheme | Replaced repetitive default charts with themed Altair visualisations, hover information, semantic colours and progress-style indicators | Makes trends and risk information easier to interpret while keeping the interface consistent with the overall theme
38 | Improved accessibility and completed final polish | Added the OpenDyslexic font option, refined page-specific CSS, fixed final layout issues and prepared the application for testing and GitHub | Improves accessibility and brings the prototype to a stable state ready for evaluation and submission